## Slide 1
Basic Block Diagram
Control Points
GUI/Web App on PC/Mobile
MQTT Client
Control Hardware
Sensors
MQTT Broker
Wi-Fi
Subscribe
Message
Publish

## Slide 2
Functional Description
GUI/Web Application will be running on PC/Mobile platform that will be communicating with Control Hardware Module via Wi-Fi Router to collect the information of the Sensors.
GUI : The GUI will be showing Zone wise information of each sensor & making logs or database for future use by GUI itself.
GUI will be having the capability to give the control command to the Relays also.
Web Application : Web Application will be working same as GUI in addition of user credential according the their hierarchy.
MQTT Broker : A MQTT broker is primarily responsible for receiving all messages, filtering them, decide who is interested in it and then sending the message to all subscribed MQTT clients. It can handle up to thousands of concurrently connected MQTT clients.
MQTT Client : A MQTT client is any device that has a MQTT library running and is connecting to an MQTT broker over any kind of network. In our case the Control hardware Module will be having the MQTT client running on it & it will be communicating with the MQTT Broker over Wi-Fi.
Control hardware Module : This hardware will be communicating with all the sensors & getting the data from them & giving that data to the GUI/WEB App over MQTT Protocol. It will be getting the control command from GUI/WEB App to configure or control the relays.

## Slide 3
ESP8266EX
NOR Flash
I2C
GPIO
Sensor 1
RTC
Sensor 2
Indicator LED (Bi-color)
Relay 2
Relay 1
Battery Monitoring
SPI
RF balun
UART
Control Hardware Module Block diagram

## Slide 4
Control Hardware Module Description
ESP8266EX : ESP8266EX is embedded with Tensilica L106 32-bit micro controller (MCU), which features extra low power consumption and 16-bit RSIC. The CPU clock speed is 80MHz. It can also reach a maximum value of 160MHz. Real Time Operation System (RTOS) is enabled. It’s having in-build Wi-Fi stack, That will be used for the communication with Wi-Fi Router.
RF balun : Wi-Fi Antenna of the Module will be connected with RF Balun of ESP8266EX.
Indicator LED : It will be a Bi-color(Red/Green) LED, That will be used for indication of the different status of the Module.
Battery Monitoring : It will be a circuit that will be used to monitor the Battery status(%) of the Module.
NOR-Flash : It will be the Flash memory used to store the application program. Theoretically, up to 16 Mbyte memory capacity can be supported in ESP8266EX.
Sensors : There will be different type of sensors according to their Zone requirement they will be connected with the Control Hardware module & giving the data to the Module & getting the commands from the Module also.
Relays : There will be different type of relays according to their Zone requirement they will be connected with the Control Hardware module & will Controlling the other Machines/Devices.
UART : It will be used for debug, Service & initial configuration purpose.

## Slide 5
Effort Estimation & Task Distribution
Engineer | Task | Task ID | Duration (Wk) | Total (Wk)
Hardware Engineer | Modules/Component Selection & procurement(Start) | H1 | 2 | 12
 | Schematic Design & Review | H2 | 2 | 
 | PCB Layout Design, Review & Modules/Component procurement(End) | H3 | 2 | 
 | Board Assembly | H4 | 2 | 
 | Board Bring-up HW Side Checks | H5 | 2 | 
 | EMC/EMI & Environmental tests | H6 | 2 | 
Firmware Engineer | Development Tool hands-on | F1 | 1 | 16
 | Test App Code Design & run on Development Board | F2 | 1 | 
 | Test App Code - Debug & Command UART bring up | F3 | 1 | 
 | Application flow Arch. & Firmware Design | F4 | 2 | 
 | Sensor, Relay, Flash Memory, RTC, LED & battery monitoring Driver/Application Development | F5 | 3 | 
 | Sensor, Relay, Flash Memory, RTC, LED & battery monitoring Driver/Application Integration | F6 | 3 | 
 | Board Bring-up SW Side Checks | F7 | 1 | 
 | Application Porting on boards | F8 | 2 | 
 | Integration with Wi-Fi Router & GUI/Web-Application | F9 | 2 | 
GUI/Web Developer | Basic Design & Review - front-end | G1 | 2 | 12
 | Final Design - front-end | G2 | 2 | 
 | Wi-Fi & MQTT driver/Application Development | G3 | 3 | 
 | Wi-Fi & MQTT driver/Application Integration | G4 | 3 | 
 | Integration with HW Module | G5 | 2 | 

## Slide 6
Milestone & Timeline
Milestone | Task | Duration (Wk)
1 | H1, H2, F1, F2, F3, F4, G1 | 6
2 | H3, G2 | 2
3 | H4 | 2
4 | H5,F5,F6,F7,G3,G4 | 4
5 | F8,F9,G5 | 4
6 | H6 | 2
 | Total | 20

## Slide 7
PC With
GUI/Web App
MQTT Client 2
Control Hardware Module 2
MQTT Broker
MQTT Client N
Control Hardware Module N
MQTT Client 1
Control Hardware Module 1
Server
Control center
Field Setup
Wi-Fi Router
I would like to use direct connection between Endpoint to gateways As shown below.

## Slide 8
ESP8266EX SDK comes with FreeRTOS integrated with that. So We will use only that because that’s already tested & verified with the module. It will decrease our production time also.
I Would like to use SVN for Coding & repository management And Mantis for bug tracking.